## Sheet1
HOTEL SOFTWARE
PHASE 1 - ANALYSIS
Date | Task | Start | Due | Notes and Comments
2013-09-10 | Requirement Gathering | 2013-09-10 | 2013-09-14
PHASE 2 - DESIGNING
Date | Task | Start | Due | Notes and comments
| Database design- | 2013-09-16 | 2013-09-21
| Form design | 2013-09-23 | 2013-10-01
PHASE 2 - DEVELOPMENT
Date | Task | Start | Due | Notes and comments
| User Module - | 2013-10-02 | 2013-10-03
User account
User access
User type
Login
Change password
Login history
| Master module | 2013-10-04 | 2013-10-07
Other charge types
Expense types
Document types
Tax master
Type of payments
Facilities
| Home Module - | 2013-10-08 | 2013-10-12
Room chart
Room display
Block rooms
| SMS- | 2013-10-14 | 2013-10-15
SMS verification
SMS Settings
| Check in- | 2013-10-16 | 2013-10-21
Personal information
Stay information
Payment information - Discount, Tax
Commission
Other charges
Uploading documents - snaps, upload, scan
| Mass Check in- | 2013-10-22 | 2013-10-24
Personal information
Stay information
Payment information - Discount, Tax
Commission
Other charges
Uploading documents - snaps, upload, scan
| Shifting rooms – | 2013-10-25 | 2013-10-26
Shift rooms
Room history
| Check out- | 2013-10-28 | 2013-10-30
Guest checkout
Refundable
Payment
Update Room status
Print
| Reservations- | 2013-10-31 | 2013-11-02
Single reservation
Mass reservation
| Expense | 2013-11-04 | 2013-11-05
Expense management
| Room master | 2013-11-06 | 2013-11-09
Room types
Add rooms
Adding rates to rooms
Facilities
Room status color
| Cash drawar | 2013-11-11 | 2013-11-15
Cash handover
Clearing CC
Owners account
| Database backup and recovery | 2013-11-16 | 2013-11-16
| Reports | 2013-11-18 | 2013-11-22
Login History reports
Checkin report
Mass checkin report
checkout report
Reservation
Block room reports
Shift room reports
Guest history report
Cash drawar
Payment report
House keeping
Don’t have requirements
PHASE 2 - SOFTWARE TESTING
| User testing | 2013-11-23 | 2013-11-26

## Marian SDLC
MARIAN PROJECTS PVT.LTD
PHASE-1 REQUIREMENT GATHERING AND ANALYSIS
Sl.No | From Date | To Date | No of Days | Notes
1 |  |  | 15(approx) | Meetings with Marian for Requirement Collection
NOTE: The Schedules for the below phases will be decided depending on the Requirement Analysis
PHASE-2 DESIGNING
PHASE-3 IMPLEMENTATION
PHASE-4 TESTING
PHASE-5 DEPLOYMENT
PHASE-6 MAINTENANCE