## Sheet1
Sl.No | Description | Hours | Status | By | Start Date | Enddate
1 | Database
a) | Requirements Collection and Database Designing | 80 | Solved
b) | Tables Creation | 16 |  | Aravind & Alaka | 2013-10-02 | 2013-10-02
| Total | 96
2 | Form Design
| Design Plannings and discussions with team | 80 |  | Aravind & Alaka | 2013-10-03 | 2013-10-08
| Main Window(Dashboard) | 24 |  | Aravind & Alaka | 2013-10-09 | 2013-10-10
a) | Master Module
| Usertypes | 4 |  | disha | 2013-10-09 | 2013-10-09
| UserAccount | 4 |  | disha | 2013-10-09 | 2013-10-09
| Other Charges | 4 |  | unais | 2013-10-09 | 2013-10-09
| Document Type | 4 |  | asha | 2013-10-09 | 2013-10-09
| Facility Types | 4 |  | asha | 2013-10-09 | 2013-10-09
| Payment Types | 4 |  | prajna | 2013-10-09 | 2013-10-09
| Company details | 8 |  | nauraz | 2013-10-09 | 2013-10-09
| Tax | 4 |  | prajna | 2013-10-09 | 2013-10-09
| Travel Agent | 8 |  | alaka | 2013-10-11 | 2013-10-11
| Unique ID | 6 |  | prajna | 2013-10-10 | 2013-10-11
| Messages | 4 |  | aravind | 2013-10-11 | 2013-10-11
b) | USER MODULE
| Login | 4 |  | disha | 2013-10-10 | 2013-10-10
| Change Password | 4 |  | disha | 2013-10-10 | 2013-10-10
| Login History | 6 |  | prajna | 2013-10-10 | 2013-10-11
| User Access | 16 |  | Aravind & Alaka & Prajna | 2013-10-12 | 2013-10-12
c) | Room MODULE
| Room Types | 6 |  | nauraz | 2013-10-10 | 2013-10-11
| Rooms | 6 |  | prajna | 2013-10-10 | 2013-10-11
| Room Facilities | 6 |  | nauraz | 2013-10-10 | 2013-10-11
| Room tariff | 6 |  | nauraz | 2013-10-10 | 2013-10-11
| Room Tax Configuration | 6 |  | asha | 2013-10-10 | 2013-10-11
| Tariff Discount | 6 |  | asha | 2013-10-10 | 2013-10-11
| Block Rooms | 6 |  | asha | 2013-10-10 | 2013-10-11
| Room Status Color | 8 |  | prajna | 2013-10-12 | 2013-10-12
d) | CHECK-IN / RESERVATION
| Guest Personal Details | 16 |  | asha | 2013-10-12 | 2013-10-14
| Guest stay Information | 16 |  | disha | 2013-10-11 | 2013-10-12
| Guest Document Information | 16 |  | nauraz | 2013-10-12 | 2013-10-14
| Guest Check in(Single) | 16 |  | unais | 2013-10-10 | 2013-10-14
| Guest Check in(Mass) | 16
| Check in Payments(BILLS& RECIEPTS) | 8
| Commission Payments | 6
| Other charges payment | 6
| Reservation(Single) | 12
| Reservation(Mass) | 12
e) | Accounts
| Expenses | 6
| Cash Drawer | 8
f) | Reports
| Room Chart | 6
| Guest Information | 4
| CheckIn Details | 6
| Payment Details | 4
| Commission Details | 4
| Expense Details | 4
| Travel Agent | 4
| Block room | 4
| Shift rooms | 4
| Pending payment | 4
| Refundable | 4
| Monthly Reports | 6
| Daily Tariff | 4
g) | Database
| Database Backup and document backup | 8
| Total | 442
3 | Development
| Development Plannings and discussions with team | 40
| Database connection,Functions,Variable Declarations | 24
| Main Window(Dashboard) | 78
a) | Master Module
| User Type | 6
| user A/C | 6
| Other Charges | 6
| Document Type | 6
| Facility Types | 6
| Payment Types | 6
| Company details | 6
| Tax | 6
| Travel Agent | 6
| Unique ID | 6
| Trail | 4
| Messages | 4
b) | USER MODULE
| Login | 6
| Change Password | 6
| Login History | 8
| User Access | 80
c) | Room MODULE
| Room Types | 18
| Rooms | 32
| Room Facilities | 18
| Room tariff | 40
| Room Tax Configuration | 24
| Tariff Discount | 24
| Block Rooms | 16
| Room Status Color | 8
d) | CHECK-IN / RESERVATION
| Guest Personal Details | 32
| Guest stay Information | 48
| Guest Document Information | 48
| Mobile No Verification | 26
| Guest Check in(single) | 84
| Guest Check in(MassCheckin) | 44
| Advance Payments | 32
| Refundable Payments | 32
| Check in Payments(BILLS& RECIEPTS) | 72
| Commission Payments | 18
| Other charges payment | 18
| Reservation(single) | 20
| Reservation(Mass) | 20
| Payment Calculations | 72
| Shift Rooms | 24
| Block Rooms | 18
| Guest Checkout | 32
e) | Accounts
| Expenses | 16
| Cash Drawer | 40
f) | Reports
| Block room | 16
| Shift rooms | 16
| Daily Check in | 20
| Commission | 16
| Pending payment | 32
| Refundable | 16
| Expense | 16
| Monthly Reports | 40
| Daily Tariff | 24
| Biling(Print) | 72
g) | Database
| Database Backup and document backup | 16
| Total | 1470
Testing
| Integration and setup | 8
| Main Window(Dashboard) | 4
Master Module
| User Type | 1
| user A/C | 1
| Other Charges | 1
| Document Type | 1
| Facility Types | 1
| Payment Types | 1
| Company details | 1
| Tax | 1
| Travel Agent | 1
| Unique ID | 1
| Trail | 1
USER MODULE
| Login | 1
| Login History | 1
| User Access | 1
Room MODULE
| Room Types | 2
| Rooms | 2
| Room Facilities | 2
| Room tariff | 2
| Room Tax Configuration | 2
| Tariff Discount | 2
| Block Rooms | 2
| Room Status Color | 1
CHECK-IN / RESERVATION
| Guest Personal Details | 3
| Guest stay Information | 4
| Guest Document Information | 4
| Mobile No Verification | 4
| Guest Check in(single) | 3
| Guest Check in(MassCheckin) | 3
| Advance Payments | 4
| Refundable Payments | 4
| Check in Payments(BILLS& RECIEPTS) | 3
| Commission Payments | 2
| Other charges payment | 2
| Reservation(single) | 2
| Reservation(Mass) | 2
| Shift Rooms | 2
| Block Rooms | 2
| Guest Checkout | 4
Accounts
| Expenses | 2
| Cash Drawer | 2
Reports
| Block room | 1
| Shift rooms | 1
| Daily Check in | 1
| Commission | 1
| Pending payment | 2
| Refundable | 2
| Expense | 2
| Monthly Reports | 2
| Daily Tariff | 2
| Biling(Print) | 2
| Total | 109
| Estimated Total Man Hours | 2037

## 1st Week
Staff | Week 1 | Total hours | Available hours
09-10-2013 to 12-10-2013
Aravinda | Main Window(Dashboard) - 12 Messages - 4 User Access - 8 | 24 HRS | 24 HRS
Alaka | Main Window(Dashboard) - 12 Travel Agent - 8 User Access - 4 | 24 HRS | 24hrs
Prajna | Payment Types - 4 Tax- 4 Unique ID - 6 Rooms - 6 Room Status Color - 8 User Access - 4 | 32 HRS | 32hrs
Unais | Other Charges - 4 Guest Check in(Single) - 16 | 20 HRS | 16 HRS
Nauraz | Room Types -6 Room Facilities - 6 Room tariff - 6 Guest Document Info -16 | 34 HRS | 32hrs
Asha | Room Tax Configuration - 6 Tariff Discount - 6 Block Rooms - 6 Guest Personal Details - 16 | 34hrs | 32hrs
Disha | Usertypes - 4 UserAccount -4 Login - 4 Change Password -4 Guest stay Information - 16 | 32 HRS | 32hrs

## 2nd Week
Staff | Week 1 | Total hours | Available hours
14-10-2013 to 19-10-2013
Aravinda | Guest Check in(Mass)-16 Check in Payments(BILLS& RECIEPTS)-8 Commission Payments-6 Other charges payment-6 Reservation(Single)-12 | 48 HRS | 42 HRS
Alaka | Reservation(Mass) -12 Expenses -6 Cash Drawer -8 Room Chart -6 Guest Information -4 CheckIn Details -6 Payment Details -4 Commission Details-4 | 50 HRS | 42hrs
Prajna | Expense Details-4 Travel Agent -4 Block room -4 Shift rooms -4 Pending payment -4 Refundable -4 Monthly Reports -6 Daily Tariff -4 Database Backup and document backup -8 Payment Types -6 Tax- 6 Unique ID - 6 | 60 HRS | 54hrs
Unais | Other Charges - 6 Guest Check in(Single) - 16 Company details-6 | 28 HRS | 24 HRS
Nauraz | Room Types -18 Room tariff - 40 | 58 HRS | 54hrs
Asha | Document Type -6 Facility Types -6 Travel Agent -6 Room Tax Configuration - 24 Block Rooms -16 | 58hrs | 54hrs
Disha | Usertypes - 6 UserAccount -6 Login -6 Change Password -6 Login History-8 Trial-4 Messages-4 Room Facilities-18 | 58 HRS | 54hrs

## 3rd Week
Staff | Week 3 | Total hours | Available hours
21-10-2013 to 26-10-2013
Aravinda | Tariff Discount -24 Room Status Color -8 Expenses-16 | 48hrs | 42hrs
Alaka | Rooms -32 Commission Payments -18 | 50hrs | 42hrs
Prajna | Guest Document Information -48 Block room -16 | 64hrs | 54hrs
Nauraz | Guest stay Information - 48 Block room -16 | 64 hrs | 54hrs
Asha | Guest Personal Details - 32 Mobile No Verification - 26 | 58hrs | 54hrs
Disha | Other charges payment -18 Reservation(single) -20 Reservation(Mass)-20 | 58hrs | 54hrs

## 4th week
Staff | Week 3 | Total hours | Available hours
28-10-2013 to 2-10-2013
Aravinda | Expenses-2 Guest Check in(single)-42 | 44 | 42
Alaka | Commission Payments -3 Guest Check in(single)-42 | 45 | 42
Prajna | Block room -6 Guest Check in(MassCheckin)-44 Advance Payments -4 | 54 | 54
Nauraz | Advance Payments-28 Refundable Payments-26 | 54 | 54
Asha | Refundable Payments-6 Shift Rooms-24 Guest Checkout-24 | 54 | 54
Disha | Reservation(Mass)-2 Daily Check in-20 Pending payment-32 | 54 | 54